## Sheet1
Date | Project | Task | Context | Problem | Status
15/7/2025(Onsite) | Car Tracking Project | Downloading an LLM (DeepSeek) | Opened Kaggle Account with the work account to start writing code on it. | I couldn’t use my phone number on the work account cause I used it on my main account. | Done on Kaggle Notebooks using an API Key that helps us connect to HuggingFace
15/7/2025(Onsite) | Car Tracking Project | Find Car Issues Dataset to finetune the model | Want to find a dataset the contains the car issue describtion and solution | I couldn't find a ready dataset to fine tune the model | Failed: No datasets couldn't be found and I have to web scrape the data from the internet
15/7/2025(Onsite) | Car Tracking Project | Define a plan to collect the data Needed for the project | Cause there is no ready dataset to finetune the model the grind beings |  | Done: Defined a plan and wrote it down on a paper and currently executing phase 1
16/7/2025(Onsite) | Car Tracking Project | Start Building the Reddit WebScrapping (Part of Phase 1) | Cause there is no ready dataset to finetune the model, I had to make the webscraper | Currently the webscrapper is very basic and needs lots of modification including : Extracting the comments(solutions of each post), including multiple subreddits, need to make a small relational database where i can make a relation between each post and its commnets, and finally we will need to make extra script to clean the data before feeding it into the Cleaning and offline AI Model | Not Completed Yet: Extra Modifications could include the following Extract the previous day data instead of todays data, extract the top 3 comments of this post, make a relationship between the parent post and the children comments
17/7/2025(Onsite) | Car Tracking Project | Make a data dictionary | The initial data that has been extracted from the reddit has lots of columns whose names are vague |  | Done: The dictionary has been made successfully, although I could add more descriptive columns like: data type, uniqueness, derived from, owner( data engineering team), ETL process(How data is populated; e.g., Daily API pull from reddit), Analytical use, known issues, last updated, change log. These changes are currently non essential therefore i will consider this step DONE.
17/7/2025(Onsite) | Car Tracking Project | Modify the WebScraper to take the previous day data now today's data. | This strange change is due to the fact we need comments on each post, and sadly when the post is new, the number of commnets on that post is almostly zero or one, which is not enough for the model to get the data as a Q&A pairs. |  | Partially Completed: The csv file now returns the comments
18/7/2025(Vacation) | Car Tracking Project | Verify if the data is true and idempotent for that single subreddit that you extracted the data from | Now as we have modified the starting time that we need to start downloading the data from, now we need to validate if the returned data is true and reproducable. | The system is not idempotent because of the special case that I will mention. The case happens when I run the script to get yesterday's day, then I will run it today but with yesterday's parameter also while running it today a comment might be added to a certain post, therefore ruining the idempotency of the script, therefore the data pipeline might produce non reproducable data, which might cause unpredicted issues in the future. Although later on i will feed the cleaned data into an online AI model to extra clean it or even add more solution that wasnt mention. Also i have to put into consideration that i extracted the top 3 comments on each post and that i didnt extract all of the comments data for storage and cleaning ease, but the issue might arise from the no comment posts that will contain comments from other users that might comment after I run the script. Also put into consideration that it is not completly logical to make a cumulative data design for here due to the problem structure. Also putting into consideration that I will run the fetching/extracting script once a day in the final pipeline, leading to no redundancy (Needs testing to a certain extend. A more formulated way to describe the issue is the following: [Potential Issues & Fixes 1. Comments Added After Initial Scrape 1.1.Problem: If a post from yesterday gets new comments today, rerunning the script would either: 1.1.1.Skip the post (if using existing_ids), missing new comments. 1.1.2.Refetch comments, breaking idempotency. 1.2.Solution: 1.2.1.Freeze comments at first scrape (store first_scraped_at). 1.2.2.OR use a separate "comment updates" script (if tracking changes is critical). (THE SOLUTION THAT I PREFER FOR SUCH AN ISSUE) (FUTURE WORK WHEN YOU MAKE THE DWH THAT WILL INCLUDE ALL OF THE CLEANED DATA). 2. Timezone Edge Cases 2.1.Problem: If the script runs near midnight UTC, some posts might be missed or duplicated. 2.2.Solution:Use fixed UTC day boundaries: python solution code( Might need modifications) yesterday = datetime.utcnow() - timedelta(days=1) start_timestamp = int(yesterday.replace(hour=0, minute=0, second=0).timestamp()) end_timestamp = int(yesterday.replace(hour=23, minute=59, second=59).timestamp()) 3. Reddit API Pagination Limits 3.1.Problem: If yesterday had >500 posts, the script might miss some. 3.2.Solution: 3.2.1.Keep MAX_POSTS = 500 but log warnings if nearing the limit and include the warning in a new metadata file. (THE SOLUTION THAT I PREFER FOR SUCH AN ISSUE) (THIS ISSUE WILL NEED LOTS OF EXTRA WORK THAT WOULD DELAY THE MAIN PROJECT GOAL WHICH IS THE LLM FOR CAR ISSUES CHAT BOT/ EMERGENCY CHAT BOT/ MECHANIC HELPER CHAT BOT). | DONE: solve problem 2 because that was the most determental issue. Solve it by implementing hard coded timestamps.
18/7/2025(Vacation) | Car Tracking Project | Move the top_comments column to the final column in the csv file. | Readability issues while working with the csv file |  | DONE
18/7/2025(Vacation) | Car Tracking Project | Modify the top_comments column into a more readable format. | Readability issues while working with the csv file |  | DONE
19/7/2025(Remote) | Car Tracking Project | Make your code extract data from multiple subreddits (Big Optimizations might be needed) | Currently the code extracts the yesterday's data from a single subreddit starting from 0:0 am till 23:59 pm. The code at this stage take 3 to 10 minutes to run, and I run the code manually no orchestration made yet. Also the current code returned maximum of 500 posts per day/run. | The most detrimental issues for me are 1. Reddit API Rate Limiting (Add the needed delays) 2. Reddit’s "After" Pagination Limit (if the subreddit does not have the 500 post or reached the end of its post then go to the next subreddit in the list) 3. Comment Fetching is Slow( Take the posts that has comments in it ). | DONE: Although it took a lot of time and it was the hardest of the previous tasks. Extra thing to look for in the upcoming day: The data volume when you include the full subreddits list that you are intersted in. The current update included getting 3 days worth of data, that will need to change before production cause we dont want any duplicate data.And tomorrow we will need to put the final touches before starting to clean and migrate the data to a database or a data warehouse. Current script returns around 1500 post and there top 3 comments (and at least one comment) for the 5 subreddits that were included.
20/7/2025(Remote) | Car Tracking Project | Add the complete list of subreddits that you collected in the planning phase. |  |  | DONE
20/7/2025(Remote) | Car Tracking Project | Download Airflow for orchestration | After successfully expanding the Reddit scraper to handle multiple subreddits (producing ~1,500 posts with comments daily), the next critical step was to automate this pipeline using Apache Airflow. The goal was to: Schedule daily runs at 11 pm egypt time Handle failures gracefully (API rate limits, network issues) Prepare for future DWH integration | Dependency Hell Conflicts between Airflow’s requirements and your Reddit scraper (praw, pandas) Docker networking issues on Windows (port conflicts with WSL2) Database Migration Errors Idempotency Concerns Airflow’s retry mechanism clashed with your custom comment-freezing logic Needed to ensure each DAG run: Skipped already processed posts (using existing_ids) Logged new comments separately (future DWH use) | NOT DONE :(
21/7/2025(Remote) | Car Tracking Project | Finalize Airflow Setup and DAG Integration | After preparing a Reddit scraper capable of collecting ~1,500 posts (with top comments) from multiple subreddits, the next step was to automate this pipeline using Apache Airflow. The plan was to create a production-ready orchestration setup with: Scheduled daily runs (target: 11 PM Egypt time) Retry and failure handling (e.g., API rate limits, network issues) Support for future database or data warehouse integration Idempotent execution (no duplicates, track scraped post IDs, etc.) | Airflow Dependency Conflicts – Issues between Airflow's core requirements and those of the Reddit scraper (e.g., praw, pandas) made setting up the environment painful. Docker Volume Mounting Issues – Although the DAGs were present locally, they didn’t appear inside the containers. This broke DAG discovery and wasted hours debugging paths, mounts, and permissions. Lack of DAG Visibility in UI – Even after confirming the DAG files existed, they didn’t appear in the Airflow UI due to improper volume setup or internal misrouting. Time-Consuming Workarounds – Fixing each part (volumes, environment conflicts, UI debugging) consumed the entire day and part of the previous one. | DONE – Airflow is now installed, running, and nearly production-ready. However, this step cost 1.9 days due to a mix of ecosystem instability, Docker-Windows edge cases, and steep Airflow setup requirements.
22/7/2025(Onsite) | Car Tracking Project | Finish setting up Prefect + GitHub Actions as an alternative orchestration tool | After two frustrating days trying to install and configure Apache Airflow, it became clear that its dependency complexity and local setup challenges would consume too much time—especially considering the main project goal is building a car-diagnosis LLM, not infrastructure experimentation. Given the tight timeline and the fact that the extraction and cleaning scripts were already manually runnable, I pivoted to Prefect for its Python-native structure, cloud-based scheduling, and smoother integration with GitHub Actions. This change aligns better with the project's simplicity-first philosophy during prototyping and offers a gentler learning curve. Additionally, GitHub Actions was chosen for its ability to trigger daily data extraction via CI/CD, enhancing automation without needing self-hosted infrastructure. | Each script (scraper, cleaner, etc.) was previously built in an ad-hoc, local way with minimal modularity and no clear interface for orchestration. In order to integrate them with Prefect and GitHub Actions, I had to: Modularize the scripts to expose main functions Improve logging and error handling Add configuration via .env or parameters for flexibility Create reusable Prefect flows and GitHub workflows that can be scheduled and monitored Reproduce the same behavior and logs from the CLI when triggered through GitHub This restructuring also had to preserve all existing features like: Extracting from multiple subreddits Next page has no posts from yesterday Next page has mixed days, only collect yesterday Less than 500 posts available | Partially Completed: The idempotency results or the main features and their idempotency errors needs extra checking Condition Status Notes Extract from multiple subreddits ✅ Fully Met No issues. Stop when next page has no posts from yesterday 🟡 Partial You filter, but don’t stop early. Add a check for all irrelevant posts. Only collect posts from yesterday if mixed days ✅ Fully Met Correct filtering. Accept fewer than 500 posts, no older-day spillover 🟡 Partial Filtering works, but no early exit when all new posts are too old.
23/7/2025(Onsite) | Car Tracking Project | Add debugging counters so that you can track the progress and the pressure that you apply on reddit's api |  |  | DONE
23/7/2025(Onsite) | Car Tracking Project | Test if the counters are working well when you change the t param from params dictionary from week to day |  |  | DONE: day param output with the selected columns: === Debugging Counters === total_posts_fetched: 11792 posts_filtered_time: 10855 posts_filtered_comments: 41 comments_skipped: 715 valid_posts_stored: 665 Completed in 15.40 minutes week param output with the selected columns: === Debugging Counters === total_posts_fetched: 11875 posts_filtered_time: 10938 posts_filtered_comments: 41 comments_skipped: 715 valid_posts_stored: 666 Completed in 15.15 minutes Not that big of a difference, need to understand the underlying logic of the built in functions more. Currently at this stage I care about getting the MVP. Next step: automate the extraction process using prefect and github actions, then find a way to clean the unstructured textual columns in the extracted csv files.
24/7/2025(Onsite/Remote) | Car Tracking Project | Modularize the Extractor code so that you can scale the project later on |  |  | DONE
26/7/2025(Remote) | Car Tracking Project | Make the script that will feed the data into The offline AI model and get its response and store it in CSV file | Now that the data is being collected, we will need to find the right tool to clean out the data, espically the car problem and the comments suggesting a solution for it. | Some of the possible options was to use ChatGPT's or DeepSeek's official api to do such a job but sadly we don’t have the money to do so; therefore, extra extra research is needed to download one of the LLM into my device locally so that I can clean the data collected from reddit. | NOT DONE :(
27/7/2025(Remote) | Car Tracking Project | Find the right LLM that would work locally well | The possible options are: DeepSeek Coder, OpenChat, Mistral 7B, or LLaMA2/3 (depending on GPU support) |  | DONE: deepseek model downloaded and will be used for the data cleaning
28/7/2025(Remote) | Car Tracking Project | Try to make the prefect and the github actions to run the scripts daily without my need to run it manually |  | While changing my code on a branch, the merged it into a the main branch by a mistake; therefore all of todays progression is gone. And I will have to modularize the code again. | FAILED REALLY HARD
29/7/2025(Onsite) | Car Tracking Project | Recover stable working version of the code | Identify and revert to the last working version of the pipeline | Although previous commits had descriptive messages, they lacked clarity. Improved commit discipline is needed. | DONE and the pipeline manual run on github is working perfectly الحمد الله The run took around 18 to 19 minutes to finish
29/7/2025(Onsite) | Car Tracking Project | Test the Reddit scraping pipeline locally | Use run_pipeline.py as the entry point from the main directory |  | DONE: The run took around 18 to 21 minutes
29/7/2025(Onsite) | Car Tracking Project | Schedule autonomous extraction via GitHub Actions | Configure the workflow to run automatically at 12:40 AM Egypt time | To validate correct UTC offset and time zone consistency | DONE Confirmed: autonomous execution triggered on time.
30/7/2025(Remote) | Car Tracking Project | Save output data automatically to data/raw/ | Ensure every autonomous or manual run writes results to data/raw/ subdirectory | Must ensure idempotency and avoid duplicate records across days | DONE: But the idempotency checks are not super complete yet, therefore we will check the ids of the post in the upcoming phase before feeding the data to the offline ai model. Before AI processing, introduce a lightweight deduplication mechanism (e.g., store post_id, scraped_at in metadata).
30/7/2025(Remote) | Car Tracking Project | Begin building the offline AI model pipeline | Develop a modular offline cleaning script to process data/raw/ and save cleaned output to data/cleaned/ | Will require I/O handling, LLM prompt formatting, and validation checks | Partially Done: Initial architecture planned and flow.py structure drafted
30/7/2025(Remote) | Car Tracking Project | Make a GitHub branch and structure the directories as planned | You will need to test the old pipeline before making any modifications |  | DONE: Old pipeline tested and worked perfectly, and the new branch is created for phase two
30/7/2025(Remote) | Car Tracking Project | Make the super comprehensive roadmap for the full project | After making 3 roadmaps combine the needed parts: Combine 3 ROADMAPS and FILE STRUTURES and MindMaps |  | DONE
31/7/2025(Onsite) | Car Tracking Project | Design a Comprehensive Execution Plan for the LLM Cleaner (Phase 2) | While reviewing the existing roadmap, I found it provides a solid high-level direction but lacks actionable detail on how to execute the offline LLM cleaning pipeline—particularly how it integrates with GitHub workflows. Today’s focus was to fill in those missing specifics. | A key challenge emerged when attempting to upload the quantized LLM model to GitHub to enable a fully online workflow. GitHub’s file size limits and runner constraints made this infeasible. This broke the assumption that the entire pipeline could run in the cloud autonomously, revealing the need for an offline/hybrid execution path that would rely on my device being powered on at certain steps.
31/7/2025(Onsite) | Car Tracking Project | Write the script that will download the model locally |  |  | DONE: The code has been written and the model has been downloaded
31/7/2025(Onsite) | Car Tracking Project | Know the inputs and outputs of each phase and what happens at each phase |  |  | DONE: The folder explaining this point is stored at Car_Clinic_Project/docs/Project Understanding Questions.docx
2/8/2025(Remote) | Car Tracking Project | Search more about together ai and how to implement it in the pipeline | After downloading the offline ai model and finishing the initial script, the script took 2 minutes for each row. And we have approcimately 10 folders, each containing around 600 rows; therefore, the amount of time needed to clean that data Is tremendous. Therefore, i tried to look for alternatives. |  | DONE: The search session is done, the same issue as before no free model that can handle the needed amount of data and I don’t want to waste time on a limit platform accesses
2/8/2025(Remote) | Car Tracking Project | Search more about free ai apis to get this unstructured data |  |  | DONE: the possible options are Kaggle notebooks, Ollama in Github actions, Hugging face inference api, and lots of paid options
3/8/2025(Remote) | Car Tracking Project | Make a educated decision on what model is accessible in your case |  |  | DONE: The decision is made:I will use ollama from github actions to clean the daily data, and for the previously extracted data make a script that runs on kaggle notebooks for speed to clean your previous data
3/8/2025(Remote) | Car Tracking Project | Update the extraction limits for faster Testing |  |  | DONE
3/8/2025(Remote) | Car Tracking Project | Fix GitHub Workflow Import Errors |  | ImportError: attempted relative import with no known parent package during flow.py execution in GitHub Actions. | DONE: Reorganized Python imports and fixed relative paths to ensure smooth module imports when executed via workflows.
3/8/2025(Remote) | Car Tracking Project | Workflow Logging Improvements |  |  | DONE: Added detailed Prefect logs at every major phase: file detection, model interaction, skipping logic, and fallback handling. Ensured logs clearly explain whether today's data was found, what was processed, and how long each stage took.
3/8/2025(Remote) | Car Tracking Project | Debugged Missing CSV Detection in GitHub Runner |  | Problem: The LLM cleaner couldn’t find the raw CSV file committed earlier in the workflow. Root Cause: Timing mismatch or GitHub artifact not being saved/accessed properly during the same job/step. | DONE: Action Taken: Adjusted the workflow logic to ensure: The raw file is committed before running the cleaner. Correct working directory and filename are used. Added logging to trace file existence checks.
3/8/2025(Remote) | Car Tracking Project | Identify why the LLM isnt working in github workflow |  | Cleaning script was too slow (~2 minutes per row using ollama run mistral), making the pipeline impractical for bulk processing. | DONE: Action Taken: Diagnosed that the issue stemmed from booting the model for each row. Decided to switch to ollama-python client with a persistent local server (hosted on http://localhost:11434). Implemented the Client.chat() method for 10x+ faster row-by-row inference.
4/8/2025(Remote) | Car Tracking Project | Add the code that shows the prompt before sending it to the model |  |  | DONE
4/8/2025(Remote) | Car Tracking Project | Check if there are any errors related to the json going in or out of the model
1/8/2025(Vacation) | Car Tracking Project | Check how the medical o1 data set looked like so that you can format your data set in the same way
1/8/2025(Vacation) | Car Tracking Project | Improve the file structure and readme file to include all the needed phases.
1/8/2025(Vacation) | Car Tracking Project | Generate a fake meta data for the branches so that you can test with later on